Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 21 October 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Incident Lifecycle Management System in ServiceNow |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

The following product backlog converts the functional requirements of the proposed Incident Lifecycle Management System into prioritized user stories. Story points represent relative effort and complexity, while sprint allocation represents the planned implementation sequence (23 user stories, 80 story points, 4 sprints of 20 points each).

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Setup & Access | USN-1 | As an admin, I can set up the ServiceNow instance with users, groups and roles so that people get the right access. | 3 | High |  |
| Sprint-1 | Incident Creation | USN-2 | As a user, I can log an incident in the Service Portal by filling a form with short description, category and urgency. | 5 | High |  |
| Sprint-1 | Incident Creation | USN-3 | As a user, I get field validation and mandatory fields on the incident form so that complete information is captured. | 3 | High |  |
| Sprint-1 | Incident Creation | USN-4 | As a user, I receive an incident number and a confirmation email once I submit an incident. | 2 | High |  |
| Sprint-1 | Incident Creation | USN-5 | As a user, I can attach screenshots or files to my incident. | 2 | Medium |  |
| Sprint-1 | Incident Creation | USN-6 | As a user, I can raise an incident by sending an email to the support mailbox. | 5 | Medium |  |
| Sprint-2 | Assignment & Priority | USN-7 | As the system, I calculate the priority automatically from impact and urgency. | 3 | High |  |
| Sprint-2 | Assignment & Priority | USN-8 | As a support agent, I get incidents assigned automatically to the right group based on category. | 5 | High |  |
| Sprint-2 | Assignment & Priority | USN-9 | As a support agent, I can open my assigned incidents and move them to In Progress. | 3 | High |  |
| Sprint-2 | SLA Management | USN-10 | As a manager, I can define SLAs so that response and resolution time is tracked for every incident. | 5 | High |  |
| Sprint-2 | SLA Management | USN-11 | As a manager, I am notified when an SLA is about to breach so that I can escalate. | 4 | Medium |  |
| Sprint-3 | Resolution & Closure | USN-12 | As an agent, I can put an incident On Hold with a reason when waiting for the caller. | 3 | Medium |  |
| Sprint-3 | Resolution & Closure | USN-13 | As an agent, I must enter resolution code and notes to resolve an incident. | 3 | High |  |
| Sprint-3 | Resolution & Closure | USN-14 | As a user, I can confirm a resolved incident or reopen it if the issue continues. | 3 | High |  |
| Sprint-3 | Resolution & Closure | USN-15 | As the system, I auto-close resolved incidents after a set number of days using a Scheduled Job. | 3 | Medium | ________ |
| Sprint-3 | Notifications | USN-16 | As a user, I receive email notifications at every state change of my incident. | 5 | High | ________ |
| Sprint-3 | Notifications | USN-17 | As a user, I can view the status and history of my incidents in the Service Portal. | 3 | High | ________ |
| Sprint-4 | Reporting & Dashboard | USN-18 | As a manager, I can see a dashboard of open incidents by priority and state. | 5 | High | ________ |
| Sprint-4 | Reporting & Dashboard | USN-19 | As a manager, I can run reports on SLA performance and agent workload. | 3 | Medium | ________ |
| Sprint-4 | Security & Audit | USN-20 | As an admin, I can restrict access with roles and ACLs and view the audit history of changes. | 3 | High | ________ |
| Sprint-4 | Mobile Access | USN-21 | As a user, I can raise and track incidents from the Now Mobile app. | 3 | Medium | ________ |
| Sprint-4 | External Integration | USN-22 | As an external system, I can create incidents through the REST API. | 3 | Low | ________ |
| Sprint-4 | Testing & Release | USN-23 | As a team, we test all flows, fix bugs, prepare documentation and give the final demo. | 3 | High | ________ |

Sprint Summary

| Sprint | Focus | Stories | Story Points |
| --- | --- | --- | --- |
| Sprint-1 | Setup and incident creation | USN-1 to USN-6 | 20 |
| Sprint-2 | Priority, assignment and SLA | USN-7 to USN-11 | 20 |
| Sprint-3 | Resolution, closure and notifications | USN-12 to USN-17 | 20 |
| Sprint-4 | Reporting, security, integration and release | USN-18 to USN-23 | 20 |

Total Estimated Story Points: 80

Sprint Planning Rationale

Sprint-1: Build the incident intake foundation: instance setup, Service Portal incident form, validation, confirmation, attachments and email intake.

Sprint-2: Implement automatic priority, group assignment, agent queue and SLA tracking with escalation alerts.

Sprint-3: Complete the lifecycle with On Hold, resolution, user confirmation, auto-closure, notifications and status tracking.

Sprint-4: Add dashboards, reports, security (roles, ACLs, audit), Now Mobile app, REST API, testing and the final demo.

Note: Story points and sprint allocation are planning estimates and may be revised based on team capacity, dependencies and actual sprint progress.

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 26 Oct 2026 | 31 Oct 2026 |  |  |
| Sprint-2 | 20 | 6 Days | 02 Nov 2026 | 07 Nov 2026 |  |  |
| Sprint-3 | 20 | 6 Days | 09 Nov 2026 | 14 Nov 2026 |  |  |
| Sprint-4 | 20 | 6 Days | 16 Nov 2026 | 21 Nov 2026 |  |  |

Velocity:

The team plans 20 story points per sprint, and each sprint lasts 6 days. The team's average velocity (AV) per day is:

AV = velocity / sprint duration = 20 / 6 ≈ 3.33 story points per day

At this rate the full backlog of 80 story points is completed in 4 sprints (24 working days), from 26 Oct 2026 to 21 Nov 2026.

Burndown Chart:

A burndown chart is a graphical representation of work left to do versus time. The chart below shows the planned burndown: the 80 story points of the backlog reduce by 20 points at the end of each sprint and reach zero at the end of Sprint-4. The actual line is added as each sprint is completed.